## Template
Completed By:
Project Phase | Deliverable(s) | Stakeholder(s) (Who) | Key Message (What) | Purpose (Why) | Communication Method (How) | Internal Deadline | Timing of Communications (When) |  |  | Owner | Status | Notes
[7 empty] | Start Date | Frequency | End Date

## Comprehensive Example
Completed By: Dr. Hoffmann
Project Phase | Deliverable(s) | Stakeholder(s) (Who) | Key Message (What) | Purpose (Why) | Communication Method (How) | Internal Deadline | Timing of Communications (When) |  |  | Owner | Status | Notes
[7 empty] | Start Date | Frequency | End Date
Project Development | Agendas and various files for project development meetings | Internal Stakeholders (Core team) | Develop project details, goals, implementation strategies, and evaluation plans | Collaborate | In-person | 2021-04-26 | 2021-05-01 | Weekly | 2021-05-31 | Administrative Coordinators | Complete
Project Development | Project development presentation to front-line staff | Front-line Staff | Discuss evidence of intervention and selection of implementation strategies with front-line staff to establish buy-in | Persuade | In-person | 2021-05-04 | 2021-05-11 | Once | 2021-05-11 | Administrative Coordinators | Complete
Pre-Implementation | Project presentation to internal stakeholders | Internal Stakeholders (Core team) | Introduce project with internal stakeholders, discuss goals and processes, and confirm approval | Consult | In-person/Virtual | 2021-05-11 | 2021-05-18 | Once | 2021-05-18 | Administrative Coordinators | Complete
Pre-Implementation | Project presentation to external stakeholders | Internal Stakeholders (Multidisciplinary committee) | Introduce project to external stakeholders and discuss goals and processes and confirm approval | Engage | In-person/Virtual | 2021-05-11 | 2021-05-18 | Once | 2021-05-18 | Administrative Coordinators | Complete
Pre-Implementation | Project introduction e-mail, telephone script to introduce project, text message template | Patients | Introduce project; discuss goals and processes; gauge interest | Engage | Telephone/email/Text | 2021-05-14 | 2021-05-21 | Ongoing | 2021-11-30 | Administrative Coordinators | Complete
Pre-Implementation | Project presentation to external stakeholders | External Stakeholders (Primary care providers) | Introduce project; discuss goals and processes; gauge interest | Engage | In person/Virtual | 2021-05-17 | 2021-05-21 | Start of Project | 2021-05-21 | Administrative Coordinators | Complete
Implementation | Status report tracking document and PPT summary | Internal Stakeholders (Core team) | Review status of the project, including updates on measures related to both intervention and implementation strategies | Inform | In-person | 2021-06-01 | 2021-06-07 | Monthly | 2021-11-30 | Administrative Coordinators | Complete
Implementation | Status report tracking document and PPT summary | External Stakeholders (Primary care providers) | Review status of the project, including updates on measures related to both intervention and implementation strategies | Inform | E-mail | 2021-08-25 | 2021-06-07 | Quarterly | 2021-11-30 | Administrative Coordinators | Complete
Implementation | Project status summary report (Internal) | Internal Stakeholders (Multidisciplinary committee) | Monthly updates on intervention results and compliance with intervention | Inform | E-mail | 2021-06-14 | 2021-06-01 | Quarterly | 2021-11-30 | Administrative Coordinators | Complete
Implementation | Project status summary (External) | External Stakeholders (Primary Care Providers) | Monthly updates on intervention results and compliance with intervention | Inform | E-mail | 2021-06-16 | 2021-06-01 | Quarterly | 2021-11-30 | Administrative Coordinators | Complete
Implementation | Project status presentation (internal and external) | Internal and External Stakeholders (Multidisciplinary Committee) | Quarterly updates on intervention results and compliance with intervention | Inform | In person | 2021-06-17 | 2021-06-01 | Quarterly | 2021-11-30 | CLP | Complete